Please start this grazing plan project from tonight and treat accuracy as very important throughout the full workflow.
I have already reviewed the client brief, attachments, and follow-up answers. This is a professional GIS analysis project, not just a simple map task, so please work carefully and use both the provided inputs and your own GIS judgment. This workflow is a general guide, and I expect you to use your own logical thinking and experience where needed to improve the final result.

Project summary
We need to develop a grazing plan in QGIS for the provided farm boundary, including:

- subdivision of the land into 3 grazing sections

- slope analysis

- distance-to-water analysis

- tree cover identification

- Sentinel-2 NDVI extraction for the dates in the Excel

- grass pixel layer after removing tree-covered pixels

- support for the Excel grazing calculation sheet

- final outputs in Spanish

Important client-confirmed details
Please note these carefully:

- Farm boundary is provided in the GeoPackage

- Use a public DEM

- Tree cover should be based on image-based classification

- Use the same NDVI dates already shown in the Excel

- The 3 sections can be equal or unequal — use GIS logic and pasture suitability judgment

- Final outputs should be in Spanish

- Client does not have a water point layer

- Client also did not clearly confirm livestock assumptions, so check the Excel carefully and use the existing structure unless something is clearly missing

Your task workflow
Please check the attachments very carefully before doing anything:

- GeoPackage boundary file

- Excel workbook structure

Then proceed with this general workflow:
1. Review and prepare inputs

- Open the GeoPackage and confirm geometry, extent, and CRS

- Open the Excel workbook and understand all required fields, sheet structure, assumptions, and expected outputs

- Check whether the Excel already includes default livestock assumptions and grazing formulas

- Note all output labels/field names that should remain in Spanish

2. QGIS project setup

- Create a clean QGIS project with proper folder structure

- Use a suitable projected CRS for area/distance analysis

- Keep all layers, raster names, groups, and outputs organized professionally

3. DEM and terrain analysis

- Download a suitable public elevation dataset

- Prepare DEM properly for the site

- Derive:

  - slope

  - hillshade if helpful for interpretation

- Review whether terrain affects grazing suitability or paddock accessibility

4. Sentinel-2 data and NDVI

- Identify and download Sentinel-2 imagery for the same dates listed in the Excel

- Check cloud cover carefully

- If one exact date is not usable, use the closest clean scene and document it clearly

- Generate NDVI rasters properly for the required dates

- Compare vegetation condition across dates if needed for planning

5. Tree cover classification

- Use image-based classification / interpretation to identify tree-covered areas

- Build a tree cover layer or raster mask with reasonable logic

- Clean the result to reduce obvious noise

- Make sure the output is suitable for masking non-grass areas professionally

6. Grass pixel layer

- Remove pixels with high tree cover

- Create the final grass pixel layer

- Check visually that the output makes practical grazing sense

- Avoid noisy or fragmented output if smoothing/cleaning is required

7. Water access logic
Since the client did not provide a water point, use your GIS logic carefully here.

- First review whether there is any visible water access clue from imagery or context

- If no clear point exists, prepare a proposed water point assumption logically and document it

- Then generate the distance-to-water analysis

- This part must be done carefully and transparently because the input was not supplied by the client

8. Paddock / subdivision design

- Divide the plot into 3 grazing sections

- Do not make random equal splits unless they make practical sense

- Consider:

  - terrain

  - access

  - usable grass area

  - tree-covered exclusions

  - water access

- If unequal divisions produce a more professional and realistic result, use them

- Use your own experience and judgment here

9. Excel grazing calculations

- Populate the Excel structure based on the GIS outputs

- Check formulas carefully

- Keep all entries and logic aligned with the existing workbook format

- If there are assumptions already embedded in the workbook, preserve them unless correction is necessary

- Make sure the final spreadsheet looks complete and consistent

10. Final quality control
Before finalizing, check:

- area values

- slope outputs

- NDVI date consistency

- tree cover masking quality

- grass layer quality

- subdivision logic

- Excel consistency

- Spanish naming/output language

- professional file organization

Output expectations
The final outputs must be professional, organized, and client-ready. At minimum, prepare:

- cleaned QGIS project

- processed raster/vector layers

- 3 grazing subdivision layer

- slope analysis output

- NDVI outputs

- tree cover layer

- grass pixel layer

- distance-to-water output

- completed Excel workbook

- clearly organized final delivery folders

Work instructions

- Please start tonight

- You have around 5 to 8 days to complete this properly

- Work fully on weekends

- Accuracy is more important than speed

- Use your own logical thinking and experience

- Do not rely only on this note — inspect the files and think like a GIS consultant

- Please check the attachments very carefully before starting the actual processing

Let me know after your first review of the files and once the project setup is ready.
Thank you